## Backlog
Summary | Description | Type | Owner | Status | Date Last Updated
Palak CAC | CAC issuance for Palak. Interim: AVD path (M365 account > AVD desktop > Azure portal). | Access | Nikki / Palak | In Progress | 7/13
Maryam CAC | CAC issuance for Maryam (has active Secret). Same AVD interim path. | Access | Nikki / Maryam | In Progress | 7/13
Access to NIPR for AI team | NIPR access for Maryam, Palak and Connor so the team can work in the environment. | Access | Nikki | In Progress | 7/13
End to End discovery with Tanis & team | Figure out how development processes will work - Kickoff/TAM walkthrough: sit with Tanis, stopwatch all steps, detail the 2 manual QCs. Tanis Granier | Discovery | Maryam | Done | 7/13
Obtain ICAM Roles data from Tanis | Sample received (ICAM_Roles xlsx, ~1,622 rows, SharePoint output example). Confirm headers and field meanings (NFCD/NFM, 1-Single) against real data. | Discovery | Maryam | Done | 7/11
Provide the engineering Onboarding Guide to Palak, Maryam and Connor | Looking to understand roles and responsibilities in the current process | Discovery | Niki | Open
Project plan: critical path, risks, resource requirements | Project tracker built (requirements, schedule, risks, ROI). Keep updated weekly. | Planning | Maryam | In Progress | 7/13
Draft acceptance-criteria proposal (advise-only, confidence thresholds, parallel-run validation) | Define when AI findings can be trusted: AI recommends, humans decide. Run 2 weeks in parallel with human QC, measure false positives, then graduate categories that prove out. Who owns false-positive risk needs a government answer. | Governance | Maryam | Open
Finalize Tech Proposal for 24-July submission | The team is moving out to restructure their process to get low hanging fruit. We want the tech proposal to show how we can take a systemic approach to convert from heavy lifting to a platform/system approach. Theme 2: Pushing the level of effort over to the mission partner/app owners for self onboarding; this will help achieve scale and reduce bottlenecks. This reduces the risk from DISA PMO back to the app owners to own their compliance (but with new automation and QA tools) to support that journey. CSM can support initial readiness and outreach (instead of pushing application roles down the approval process). For scale, use 50k user applications that are onboarded onto Sailpoint by 2027. How can we break down the cost per onboarding? For performance measures, we should target 300 application onboarding from now till then (mix of CSM assisted and auto-assisted onboarding). Current vehicle: GDIT's OTA expires Dec 31 2026; there is an expected 1 year extension which will take the OTA until Dec 31 2027. | Proposal | Maryam, Palak, Connor, Matt | In Progress | 7/13
Microsoft Azure tenant & resource group call - contacts, Azure OpenAI status, Tanis onboarding test, subscription/SAR list | Schedule an intro call with Microsoft team to understand environment - what's accessible, who pays for what, what approvals are required. Outcome - what environments and list of services are available (e.g. OpenAI APIs)? E.g. AKS, VMs, data science environment. How long will it take to provision new users (Maryam, Palak and Connor?) | Environment | Niki & Roberto | Open
Review Roberto's genai.mil agent; extract QC logic for deterministic core | Take the QC logic Roberto's agent generates, make it a reusable script (generate once, deploy). Keep the LLM only for the analysis part. Avoids genai.mil token throttling. | Development | Maryam & Roberto | Open
Run offline validator against real exported role sheets | Validator is built and tested on synthetic data (10/10 tests, catches hidden characters, SOD conflicts referencing nonexistent roles, schema errors). Point it at real exports and review findings with Tanis. Demo recording done. | Development | Palak | In Progress | 7/13
Tune/extend QC rules from real-data findings | Add or adjust rules from what the real files show. All tests must stay green. | Development | Palak | Open
Bulk validation demo - upload up to 500 apps at once, pass/fail dashboard | Local website: upload a zip of role sheets, background batch run, dashboard with pass/fail per file and CSV export. Sized for the ~500 app volume. | Development | Palak | In Progress | 7/13
Read-only ingestion path from submission data (SQL or SharePoint export) | Service reads new submissions, validates overnight, never writes back. Needs one approval: read-only data access. | Development | Connor | Open
Teams notification delivery | Findings posted to Teams per submission (webhook). Reviewers see results each morning and only touch exceptions. | Development | Connor | Open
Parallel-run harness - platform vs human QC comparison | Log both outcomes for every submission for ~2 weeks. Produces the false-positive numbers behind the acceptance criteria. | Development | Connor | Open
SOD conflict graph analyzer | Graph of roles and conflicts; flags conflicts pointing at roles that don't exist, inactive roles in active conflicts, and unusual patterns with a score. | Development | Palak | Open
Azure go/no-go decision (~Jul 28) | If tenant access and provisioning are confirmed fast enough, promote the container to AKS. If not, skip it - the read-only service carries the PoP. Zero schedule risk either way. | Environment | Maryam | Open
AKS promotion prep (manifests, change request) - blocked until gate | Deployment files ready so promotion is a config exercise, not a rebuild. | Environment | Connor | Blocked
Weekly status to Matt/Nikki (Fridays) | Metrics, risk changes, asks. | Governance | Maryam | Recurring

## Schedule
Date | Milestone | Description
13-Jul | Kickoff / TAM walkthrough with Tanis | Process mapped, 2 manual QC steps detailed, resource requirements captured
16-Jul | Offline validator running on real exported files | First real defect catches - demo artifact for stakeholders (zero access needed)
19-Jul | Government provied prioritized application list
24-Jul | Tech proposal is due with pricing | Systemic/platform approach + Theme 2 self-onboarding story
28-Jul | Azure go/no-go decision | Tenant access + provisioning speed confirmed by Microsoft call, or we stay on the no-cloud path with zero schedule impact
~10-Aug | Read-only validation service operational | Every new submission validated overnight, findings to Teams, humans review exceptions only. Runs after ~2-week parallel run with human QC.
10-Aug | Government negotitaions commence
~24-Aug | Auto-triage graduation review | Categories with proven accuracy from the parallel run move from advise-only to auto-clear
9-Sep | End of Period of Performance. ~500 apps need to be onboarded | Close-out metrics package: catch rate, false positives, hours saved - evidence for definitization and follow-on
Dec 31 2026 | GDIT OTA expires | Expected 1 year extension to Dec 31 2027
Jan 1 2027 | Next Gen E-ICAM start (building to Ping stack) | Current build stays on Sailpoint; NextGen ideas parked separately
Nov-27 | Expected migration from Sailpoint ICAM to Ping/ Next Gen ICAM stack
By 2027 | Scale reference: 50k user applications onboarded onto Sailpoint | Basis for cost-per-onboarding breakdown in the proposal; target 300 application onboardings (mix of CSM assisted and auto-assisted)

## Architecture
Phase | What it is | Access needed | Status | When
1. Offline validator | Standalone tool + local website. Upload role sheets (single or zip up to ~500), get pass/fail with findings down to row and field, plus fix guidance. Catches hidden characters, missing fields, bad values, SOD conflicts pointing at roles that don't exist, duplicates. Same checks the humans do today, in seconds. | None - runs on exported files, fully offline | Built & demoed | Now
2. Read-only validation service | Same engine in a container, connected read-only to submission data. Validates everything overnight, posts findings to Teams. Never writes anything back. Humans only review flagged items - this replaces the 2 manual QC steps. | Read-only data access + one container runtime + Teams posting | Next build | Operational ~10-Aug
3. Azure IL5 (conditional) | Same container promoted to AKS in the IL5 tenant. Findings in minutes instead of overnight, scales for the CoCom wave, permanent home. Only if Microsoft confirms tenant access fast enough - otherwise Phase 2 carries the PoP. | IL5 subscription + event trigger + change request; Azure OpenAI status TBD | Gated ~Jul 28 | ~Aug if gate passes
4. Self-onboarding agent (follow-on) | Theme 2 end-state: an agent that interviews the mission partner and fills the onboarding forms for them, so errors, conflicts and anomalies never enter the pipeline. Pushes level of effort to app owners with automation + QA tools supporting them; CSM supports readiness and outreach. This is the new-contract conversation, not the 60 days. | Intake form ownership (transitioning from Microsoft to GDIT) + approved AI environment | Proposal theme | Post-PoP / NextGen
Design rules
One engine, all phases - it's the same code moving homes, not rebuilds.
Deterministic checks are authoritative; AI is advise-only until the parallel run proves it; humans decide exceptions.
Build for Sailpoint (current platform). Ping/NextGen ideas are parked.
Nothing ever modifies a submission - the platform reports, it does not change data.

## RAID Log
Type | Item | Impact | Owner / Action | Status
Risk | Azure tenant access is Microsoft-controlled; timeline unknown | Phase 3 can't happen; team access slows | Niki & Roberto - Microsoft call; Tanis onboarding used as speed test; escalate via Tracy > Carl if needed | Open
Risk | genai.mil token throttling with no quota visibility | Fallback LLM path is degraded for heavy tasks | Deterministic core minimizes LLM calls; quantify limits with a test | Open
Risk | False positives could block good submissions once auto-triage is on | Trust in the platform | Advise-only first; 2-week parallel run; government agrees graduation criteria | Open
Risk | Blazor intake form still owned by Microsoft (transition pending) | Can't fix problems at the source yet; Phase 4 blocked | Design around the form for now; Nikki tracks handoff | Open
Risk | Existing automations hitting thresholds under surge load | Instability during exactly the period we're accelerating | Locate failure points from Tanis walkthrough; scope fixes | Open
Risk | One onboarding request can hide multiple apps (bundles) | App counts and effort underestimated | Ask for bundle info in the government list | Open
Assumption | IL5 / NIPR enclave is the target environment | Drives every environment and tooling choice | Confirmed on kickoff call | Confirmed
Assumption | Sailpoint is the platform until NextGen (Ping) starts Jan 2027 | Build target | Confirmed | Confirmed
Assumption | ~500 apps in scope for the PoP; 300 onboardings targeted through 2027 | Sizing for demos, performance and pricing | Government list ~19-Jul firms this up | Open
Assumption | Read-only access to submission data will be approved | Phase 2 depends on it | Request goes in after Tanis walkthrough | Open
Issue | Palak and Maryam CACs not issued; GFP hardware months behind | Team can't work hands-on in the environment | AVD interim path; SAR paperwork started; Nikki driving | In Progress
Issue | AAP vs AAP+IDP scope unclear in the government letter | Could change deliverables | Question submitted to government (Jason) | Open
Dependency | Government prioritized application list | Defines what we validate first | Due ~19-Jul | Open
Dependency | Microsoft call outcome (environments, services, provisioning time) | Azure go/no-go on ~28-Jul | Niki & Roberto scheduling | Open
Dependency | Tanis availability for walkthrough, data questions and rule tuning | Discovery and QC accuracy | Kickoff done; ongoing | In Progress
Dependency | QC SME time (~2 hrs/week) during the parallel run | Threshold calibration | Nominate after proposal | Open